BodyCheck

AI Medical Triage App

LotusHacks 2026 × HackHarvard × GenAI Fund

VNG Campus, Ho Chi Minh City • March 20–22, 2026 • 30-Hour Build

Team of 4 • Plain HTML/CSS/JS • 6+ AI Integrations

# 1. Project Overview

BodyCheck is an AI-powered medical triage web app. Users tap a body region that hurts, describe their symptoms in text or voice, and receive an instant AI diagnosis with severity rating, recommended actions, trusted medical references, and an anatomical illustration — all readable aloud in Vietnamese or English.

## Track Alignment

| Track | Sponsor | How BodyCheck Qualifies |
| --- | --- | --- |
| Social & Mobility | TASCO | Healthcare accessibility for underserved Vietnamese communities |
| Technology & Consumer | AWS | Mobile-first AI consumer health app with voice interface |
| Enterprise | TinyFish | B2B triage API for clinics, insurers, and pharmacies |
| EdTech | ETEST | Interactive anatomy education through symptom exploration |

# 2. Tech Stack

## Frontend (Person 1 + Person 2)

| Technology | Purpose | Free? |
| --- | --- | --- |
| HTML5 + CSS3 | All UI — no framework, no build step | Yes |
| Vanilla JavaScript | All interactivity and API calls | Yes |
| Lovable.dev | AI-generate base HTML shell in minutes (sponsor) | Yes (sponsor) |
| react-body-highlighter / SVG | Clickable body map with pre-mapped regions | Yes |

## AI Services (Person 3 + Person 4)

| Service | Use in App | Get Key At | Free? |
| --- | --- | --- | --- |
| OpenRouter → Claude | Diagnosis engine (English) | openrouter.ai | Yes (credits) |
| OpenRouter → Qwen | Diagnosis engine (Vietnamese) | openrouter.ai | Yes (credits) |
| fal.ai Flux Schnell | Body region illustration | fal.ai | Yes (sponsor) |
| ElevenLabs STT | Voice symptom input (mic) | elevenlabs.io | Yes (free tier) |
| ElevenLabs TTS | Read diagnosis aloud | elevenlabs.io | Yes (free tier) |
| Exa.ai | Medical reference search | exa.ai | Yes (1k/month) |

## Infrastructure

| Tool | Purpose | Free? |
| --- | --- | --- |
| Replit | Deploy + instant public HTTPS URL (sponsor) | Yes |
| GitHub | Version control, 4 branches | Yes |
| Canva | Pitch deck (sponsor) | Yes |

# 3. Repository Structure

bodycheck/

├── index.html              ← Person 1

├── config.js               ← Person 3 (NOT committed)

├── server.js               ← Person 4 (Replit env injection)

├── styles/

│   ├── main.css            ← Person 1

│   └── diagnosis.css       ← Person 1

├── components/

│   ├── body-map.js         ← Person 1

│   ├── symptom-form.js     ← Person 2

│   ├── voice-input.js      ← Person 2

│   └── diagnosis-card.js   ← Person 1 (UI) / Person 3 (data)

├── api/

│   ├── openrouter.js       ← Person 3

│   ├── elevenlabs.js       ← Person 3

│   ├── fal.js              ← Person 4

│   └── exa.js              ← Person 4

├── state/

│   └── app-state.js        ← Person 2

├── data/

│   └── body-regions.js     ← Person 1

├── .env.example            ← Person 3 (safe to commit)

└── README.md               ← Person 4

# 4. 30-Hour Sprint Timeline

| Hour | Task | Owner |
| --- | --- | --- |
| 0–1 | Kickoff — roles, repo, API keys, .env setup | ALL |
| 1–3 | Lovable.dev scaffold → HTML/CSS shell | P1 |
| 1–3 | OpenRouter account + first test call in console | P3 |
| 3–7 | Body map SVG integration (clickable regions) | P1 |
| 3–7 | Symptom form HTML + CSS (pain type, duration, slider) | P2 |
| 7–9 | App state wiring (JS object, setters, buildPrompt) | P2 |
| 7–11 | LLM prompt + JSON parse + error handling + fallback | P3 |
| 9–11 | Diagnosis card UI (severity badge, conditions, tips) | P1 |
| 11–13 | ElevenLabs TTS — read diagnosis aloud | P3 |
| 11–14 | fal.ai — generate body region illustration | P4 |
| 14–17 | Exa.ai — medical reference search + display | P4 |
| 17–19 | ElevenLabs STT — voice input, auto-fill form | P2 |
| 19–21 | Vietnamese language mode (Qwen model swap) | P2 |
| 21–24 | Mobile CSS polish + loading skeletons + error states | P1 |
| 24–26 | Integration testing + bug fixes (all working together) | ALL |
| 26–27 | Replit deploy + public HTTPS URL | P4 |
| 27–29 | Demo video (2 min) + pitch deck (3 slides) | P4 |
| 29–30 | Rehearse demo, final check, submission | ALL |

# 5. API Keys (Hour 0 Priority)

Person 3 collects ALL keys before anyone writes API code. Keys shared via team chat (not GitHub).

| Service | Sign-up URL | Cost |
| --- | --- | --- |
| OpenRouter | openrouter.ai | $5 deposit or free sponsor credits |
| ElevenLabs | elevenlabs.io | Free (10k chars/month) |
| fal.ai | fal.ai | Free (sponsor credits at event) |
| Exa.ai | exa.ai | Free (1,000 searches/month) |
| Replit | replit.com | Free (deploy + host) |
| Lovable.dev | lovable.dev | Free (scaffold) |

## config.js (Local Only — Never Commit)

// config.js

window.ENV = {

OPENROUTER_KEY: "sk-or-v1-...",

ELEVENLABS_KEY: "...",

FAL_KEY: "...",

EXA_KEY: "...",

};

# 6. Team Responsibilities

## Person 1 — UI Lead

Stack: HTML, CSS, JavaScript

- Lovable.dev scaffold — AI-generate base layout (Hours 1–3)

- Body map integration — clickable SVG grid with front/back toggle (Hours 3–7)

- Diagnosis card component — severity badge, conditions, tips, disclaimer (Hours 9–11)

- Mobile CSS polish — responsive layout, skeleton loaders (Hours 21–24)

- Files owned: index.html, styles/, components/body-map.js, components/diagnosis-card.js

## Person 2 — Form + State + Voice

Stack: HTML, JavaScript

- Symptom form — pain type buttons, duration dropdown, severity slider (Hours 3–7)

- App state object — single source of truth, buildPrompt() method (Hours 7–9)

- ElevenLabs STT — mic recording, auto-fill symptom textarea (Hours 17–19)

- Vietnamese language toggle — swap model + translate UI strings (Hours 19–21)

- Files owned: components/symptom-form.js, components/voice-input.js, state/app-state.js

## Person 3 — AI Core

Stack: JavaScript, API integration

- Collect ALL API keys at Hour 0 — everything blocks on this

- OpenRouter LLM call — system prompt (EN + VI), fetch, JSON parse, fallback (Hours 7–11)

- ElevenLabs TTS — multilingual audio playback of diagnosis (Hours 11–13)

- window.runDiagnosis() — global orchestrator, calls all AI in parallel (Hours 10–11)

- Files owned: api/openrouter.js, api/elevenlabs.js, .env.example, config.js

## Person 4 — AI Extras + Deploy + Pitch

Stack: JavaScript, DevOps

- fal.ai integration — body region medical illustration (Hours 11–14)

- Exa.ai integration — medical reference cards from trusted domains (Hours 14–17)

- Medical disclaimer banner + footer text (Hours 23–24)

- Replit deploy — public HTTPS URL for demo (Hours 26–27)

- 2-minute demo video recording + 3-slide Canva pitch deck (Hours 27–29)

- Files owned: api/fal.js, api/exa.js, server.js, README.md

# 7. Medical Disclaimer (Required)

This exact text MUST appear in: every AI system prompt, the diagnosis card, and the app footer.

"BodyCheck is an AI tool for general information only and is not a substitute for professional medical advice, diagnosis, or treatment. If you are experiencing a medical emergency, call 115 immediately."

# 8. How to Win

## During the Demo (2 minutes)

- Open app — show body map (10s)

- Click "lower right abdomen" — form appears (10s)

- Speak symptoms via mic — ElevenLabs STT fills form (20s)

- Hit Diagnose — fal.ai image + Claude JSON both load (15s)

- Diagnosis card shows — click Read Aloud (ElevenLabs TTS) (20s)

- Scroll to Exa.ai medical sources (10s)

- Switch to Vietnamese mode (10s)

- Close with impact: "AI triage for 60% of Vietnam without doctor access" (25s)

## Sponsor Prize Stack

| Sponsor | Prize Condition | Your Hook |
| --- | --- | --- |
| fal.ai | Best use of fal.ai | Anatomical illustration generated per diagnosis |
| ElevenLabs | Best voice AI | Bilingual STT + TTS in a medical context |
| Exa.ai | Best search integration | Domain-filtered medical reference retrieval |
| OpenRouter | Best multi-model | Claude (English) + Qwen (Vietnamese) routing |
| Lovable.dev | Best AI-built UI | Entire frontend scaffolded with Lovable prompt |

Good luck. Build fast, demo confidently, tell the Vietnam story.